## GanttChart
Sharlene World | [7 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
40.015 Simulation Modelling and Analysis
| Project Start Date | 2023-02-01 |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
| Project Members | Nhieu Chia Xin Yi, Danny Yeo Rui Quan, Robin Yeo Shao Jie,Ng Jie Lin | [5 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01
 | time axis 2023-01-30 to 2023-05-07
WBS | TASK | In-charge | PREDECESSOR | START | END | DAYS | % DONE | time axis 2023-01-30 to 2023-05-07
1 | Brainstorm Ideas: |  |  |  | -
1.1 | Research on possible problems | All |  | 2023-02-01 | 2023-02-03 | 3 | 100% | bar: 2023-02-01 to 2023-02-03
1.2 | Generate a few idea based on the selected problems | All |  | 2023-02-03 | 2023-02-07 | 5 | 100%
1.3 | Evaluate all the possible ideas | All |  | 2023-02-07 | 2023-02-10 | 4 | 100%
1.4 | Select the most suitable idea | All |  | 2023-02-07 | 2023-02-10 | 4 | 100%
2 | Define the concept and game mechanics: |  |  |  | -
2.1 | Conduct deeper research to gain better indsight | All |  | 2023-02-10 | 2023-02-14 | 5 | 100%
2.1.1 | Understaning the queuing behaviours in the theme park | Jie Lin |  | 2023-02-10 | 2023-02-14 | 5 | 100%
2.1.2 | Understanding the layout, type of vistors, type of attractions in the theme park, | Robin |  | 2023-02-10 | 2023-02-11 | 2 | 100%
2.2 | Collect theme park data and summarise the data | Xin Yi |  | 2023-02-11 | 2023-02-22 | 12 | 100%
2.3 | Based on the research, identify the core mechanics of the simluation | All |  | 2023-02-22 | 2023-02-26 | 5 | 100%
2.4 | Determine the parameters to be used in simulation based on summarise data | All |  | 2023-02-22 | 2023-02-26 | 5 | 100%
2.5 | Put together bibliography and summary of literature | Jie Lin, Robin |  | 2023-02-27 | 2023-03-01 | 3 | 100%
2.6 | Finalise the textual description of project | All |  | 2023-03-01 | 2023-03-03 | 3 | 100%
3 | Plan the simulation design |  |  |  | -
3.1 | Simulation Layout | All |  | 2023-03-03 | 2023-03-09 | 7 | 100%
3.2 | Scoring system for simulation | All |  | 2023-03-10 | 2023-03-16 | 7 | 100%
3.3 | Simulation details and logic | All |  | 2023-03-10 | 2023-03-16 | 7 | 100%
3.4 | Draw state diagram | All |  | 2023-03-17 | 2023-03-18 | 2 | 100%
4 | Develop the simulation |  |  |  | -
4.1 | Develope a simulation | Danny |  | 2023-03-20 | 2023-04-18 | 30 | 100%
4.2 | Test the simulation | Danny |  | 2023-03-20 | 2023-04-18 | 30 | 100%
4.3 | Debug the simulation | Danny |  | 2023-03-20 | 2023-04-18 | 30 | 100%
5 | Output anaylysis |  |  |  | -
5.1 | Identify variable we want to measure | Xin Yi |  | 2023-02-22 | 2023-02-26 | 5 | 100%
5.2 | Identify the suitable output analysis model for our simulation | Xin Yi |  | 2023-03-03 | 2023-03-09 | 7 | 100%
5.4 | Gather and analyse the output data | Robin |  | 2023-04-19 | 2023-04-28 | 10 | 100%
6 | Final Deliverables |  |  |  | -
6.1 | Create slide to document our programming code & modelling | Jie Lin |  | 2023-03-20 | 2023-04-23 | 35 | 100%
6.2 | Create Video | Jie Lin |  | 2023-04-18 | 2023-04-22 | 5 | 100%
6.3 | Complete and compile other deliverable | Xin Yi, Robin |  | 2023-03-30 | 2023-04-28 | 30 | 100%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).